# Attachment C: Creating Community Clinical Linkages to Heart Health Work Plan

October 1, 2024 – June 30, 2025 (first year only)

## Project Objectives

Objectives are major steps the program will take to reach its goal of reducing disparities and improving heart health outcomes in the chosen category. Ensure that each objective is SMART:

Specific: concrete and well-defined

Measurable: can determine what changed and how much it changed

Achievable: feasible to put into action

Realistic: considers constraints such as resources, personnel, cost, and time frame

Time-Bound: time frame for the objective

One way to create an objective is, “By (date), (amount of change) of (what population) will (action of change).”

### Project Strategies

For each objective, specify strategies. Strategies are general approaches to meet an objective. Think of strategies as the “how” of the project while activities are the “what.”

### Project Activities –Work Plan Tables

The work plan tables must include all activities planned for the first fiscal year. The sustainability section allows you to describe future activities for years 2 and 3. Activities are the “what” of the project to accomplish the “how” of the strategies. For each activity, include the: activity, staff and community partners involved, start and end date, and outputs.

## Example:

Category 2: Culturally responsive education and/or support for chronic condition prevention, screening, follow up, and/or self-management:

Objective: By June 30, 2025, 20% of Hmong patients with hypertension will be referred to a culturally tailored support for chronic condition follow up and self-management.

Strategy: Provide education on a local Hmong walking group.

| Activity | Lead Person & support staff | Partners Involved | Timeline | activity output |
| --- | --- | --- | --- | --- |
| Example: Create handout with culturally tailored supports to refer to | Example: Project Manager & Community Health Worker | Example: Clinic X, Community Organization Y | April 2025-June 2025 | Example: # culturally tailored supports available # of referrals made |

Sustainability Plans for Years 2 and 3: Briefly describe plans for years 2 and 3 here.

## Note: Add headings, rows and tables as needed to align with your project on page 2.

Grantee Organization:

Project Name:

Category:

Population(s) Served:

Category:

Objective:

Strategy:

| Activity | Lead Person & support staff | Partners Involved | Timeline | activity output |
| --- | --- | --- | --- | --- |
| Enter activity here | Enter name(s) here | Enter partner(s) here | Enter timeline here | Enter activity output here |

Sustainability Plans for Years 2 and 3: